## CHNA_ImplPlan_Draft
2022 CHNA Implementation Plan - Carroll County (IA) on behalf of MRHC
Wave #4 2022 CHNA Health Needs Tactics - Year 1 of 3 (Starting 7/1/22 – 6/30/23)
| CHNA Health Areas of Need |  | "Specific Actions" to Address Community Health Need or "Reasons Why Hospital Will Not" | Findings/Results of Actions | Identified "Lead" | Identified Partners | Timeframe | $$$
1 | Mental Health / Suicide Services |  |  |  | MRHC (Senior Life Solutions) / New Opp | Schools, Church, City, County, DOH, Law Enforcement | 7-1-2022 to 6-30-2023
|  | a | Continue depression screenings by primary care physicians. Add trauma assessment for pediatrics and other MH issues. | Ongoing | Subcommittee: Shelby Dickson, Michelle Andersen, Janet Brus, Christy Jenkins | Subcommittee: Megan Reis, Pastor Conner | “
|  | b | Continue MRHC Senior Life Solution's programs and local transport services for Mental Health patients. | Ongoing |  |  | “
|  | c | Continue promoting existing mental health services, facilities and providers. Educate community on placement process and options. | Ongoing. Added Hollie Schechinger counseling patients 2xweek. Added Brian Paugh PA-C tx through telehealth. |  |  | “
|  | d | Continue to investigate other grant writing opportunities to fund mental health. Use grant funding to support mental health care and mental health prevention. | Ongoing |  |  | “
|  | e | Collaborate with community elementary, middle, and high schools to educate students on mental health and suicide to begin designating mental health conditions. | Ongoing |  |  | “
|  | f | Continue WIC Screening Program for all kids (state-wide) ages 0-5 years old and use other department/screening tools. | Ongoing |  |  | “
|  | g | Conduct a physician manpower assessment to identify number of Mental Health providers needed. Recruit Mental Health providers to meet specific mental inventory needs. | Ongoing |  |  | “
|  | h | Explore providing mental health service "first aid" training for law enforcement, schools, and other first responders in the community. | Ongoing |  |  | “
|  | i | Explore offering a suicide prevention training at and in partnership with schools. Develop and sponsor an anti-suicide campaign for local community members. | Ongoing |  |  | “
|  | j | Continue to promote 24-hour crisis hotline (Statewide Number: 1-800-273-8255 or 1-800-784-2433). | Ongoing |  |  | “
|  | k | Enhance follow-up care to raise awareness of the resources available in the community for Mental Health / Suicide. | Ongoing |  |  | “
|  | l | Explore potential space for additional MH services within the hospital. (Recovery Center) | Done with the addition of Hollie Scheckinger's office. |  |  | “
|  | m | Continue Suicide prevention training at schools. Develop and sponsor an anti-suicide campaign for local community members. Initiate implementing an anti-bullying program at the local schools for support / prevention for the youth. | Ongoing |  |  | “
|  | n | Explore hosting Suicide Prevention Public service announcements, literature, resources to contact (Availability). Providers identifying and promoting services, education, etc. | Ongoing |  |  | “
2 | Ambulance Staffing | a | Continue to promote ambulance/paramedic training programs done by other communities and adopt their successful approaches to recruit/retain and train staff. | Ongoing | Carroll County (CC) Ambulance Service | MRHC, DMACC, WIT, IWCC, City, Neighboring Counties | “
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Continue to encourage and collaborate with Community College Internship programs to & educate young adults on EMT and Ambulance safety and need in PSA. | Ongoing | Subcommittee: Kenny Hansen | Subcommittee: Jean Voege, Mikasia Jacobsen, Dawn Meyer | “
|  | c | Market ambulance training programs to graduating high schoolers. Recruit grads to EMS careers. | Ongoing |  |  | “
|  | d | Continue developing partnerships with surrounding communities to 'share' ambulance staff when shortages occur. | Ongoing |  |  | “
|  | e | Continue to provide continuing education to all existing ambulance staff to ensure the most up to date protocols are known / followed. Test Skill level yearly. | Ongoing |  |  | “
|  | f | Continue Carroll County training and recruiting processes. Seek new volunteers in PSA to staff the ambulance services. | Ongoing |  |  | “
|  | i | Explore the idea of Silver Cords through the High School to encourage more community services. | Ongoing |  |  | “
|  | j | Continue to provide financial support to EMS volunteers that meet a certain volunteer hour threshold per year | Ongoing. Several nurses are getting financial incentives for their ambulance service time. |  |  | “
3 | Lack of Rural Healthcare Reimbursement | a | Continue to reach out to local politicians to understand their healthcare delivery agenda. Encourage Rural Health Reform. | Continuing to do. | MRHC / IHA | State, City, Economic Dev. | “
|  | b | Increase policy advocacy efforts with other independent CAH's | Ongoing | Subcomittee: Linn Block, Amy McLaughlin | Subcommittee: Dawn Rohe | “
|  | c | Partner with IHA on their initiatives. Participate on IHA health initiative task force. Participate in IA advocacy work. | Ongoing |  |  | “
|  | d | Sponsor hospital tours for local, state and US Congressman. Set up a Town Hall session each time they come. | Ongoing |  |  | “
|  | e | Research tuition reimbursement options for providers in rural communities (Apply star designation to provide reimbursement). Advertise this option to specialists as a recruitment tactic. | Ongoing |  |  | “
4 | Obesity (Nutrition / Exercise) | a | Encourage/sponsor a hospital or community-wide "fitness challenge" focusing on fitness, nutrition, and physical activity for members of all ages. Give out free water bottles at event. | Ongoing | MRHC | DOH / CCWellness Coalition, Schools, City, County, Law Enforcement, New Opportunities | “
|  | b | Educate local businesses and industries on the benefits of offering wellness programs for their employees. Promote discounted recreational memberships / corporate memberships. | Ongoing | Subcommittee: Julie Hodne | Subcommittee: Amber Schon, Maggie Pauley, Cory Arp | “
|  | c | Increase & promote access to healthy foods in schools for youth and nursing homes for seniors. Provide healthier school vending options. | Ongoing |  |  | “
|  | d | Work with New Opportunities using the FRESH TOUR TRAILER Campaign with new grant funds. This includes cooking demos, food labels, grocery store tours, restaurants healthy meals / portions options, health fairs, classes, speakers etc. Continue to collaborate w/ local schools and daycares to promote & cook "healthy meals". | Ongoing |  |  | “
|  | e | Continue to market and promote the local farmers market and community gardens. Use social media, radio, and newspaper to expand and grow vendors. | Ongoing. Local grocery store closed spring of 2023. Farmer's Markets on Friday afternoons and Willow Creek Market Garden has been helpful providing fresh produce to PSA. |  |  | “
|  | f | Maintain the local food pantry and encourage healthy choices and fresh produce. | Ongoing |  |  | “
|  | g | Sponsor community activities that promote physical fitness/exercise for the entire family such as a 5ks, children's sports or activities. | Ongoing |  |  | “
|  | h | Continue with building and improving the walking/ biking trails in PSA. Create water fill stations throughout wellness areas of PSA including on the trails. | Ongoing. New cement poured on trail from MRHC to Great Western Park. |  |  | “
|  | i | Continue “Awareness Program” to educate elementary/middle school children and their families about healthy lifestyles. | Ongoing |  |  | “
|  | j | Continue partnership with Manning Police that teach safety tips and hand signals to youth who ride bikes. Continue MRHC partnership and safety classes. Have promotion premiums to give away at the event. | Ongoing |  |  | “
|  | k | Continue to promote / provide "free and/or low cost" sports physicals / wellness examinations for the school & parents. Additionally, continue Medicare wellness outreach. | Ongoing |  |  | “
|  | m | Continue to provide and work on "Occupational Health Flyer" offerings / education to employers through work-site health fairs and/or educational programs, including various screenings. | Done. See link. |  |  | “
|  | n | Develop a partnership between the schools and Rec Center so area children can go to the Rec Center to exercise. Partner with the City Parks and Recreation Dept to encourage additional opportunities throughout PSA. | Ongoing. The Manning REC Center provides many activities for youth & adults. They are always looking into new programs to offer. |  |  | “
|  | o | Explore sponsoring a (New Opportunities) program to teach people how to shop on a budget and eat 'healthy. Continue hosting Dining with Diabetes for nutrition education. Research having an “Awareness Program” to educate elementary/middle school children and their families about obesity | Ongoing |  |  | “
|  | p | Maintain inventory through a resource guide (hours / programs) of fitness centers in Carroll County. Continue to promote fitness activities within the community - Zumba, water aerobics, family swim, etc. utilizing the community calendar and DOH social media page. | Ongoing |  |  | “
5 | Senior Care | a | Continue supporting senior activities (Manning Senior Center) and work together to establish new senior activities / programs for them to engage in. | Ongoing - part of a cohort - have had meetings and a plan for the next step in a small group setting. | PSA Nursing Homes / LTC / AL / Sr. Housing | MRHC, Rehab Thereapy, City, Manning Senior Center, WIT, Elderbridge. | “
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Explore starting the a "Adopt a Senior" Program in the county. | Ongoing | Subcommittee: Michelle Andersen, Julie Hodne, Brittany Martz | Subcommittee: Mindi Boyle, Kathy Schwaller & Cory Arp | “
|  | c | Conduct feasibility study to document need of senior services and staffing/development. | Ongoing |  |  | “
|  | d | Explore the expansion of senior transportation services while looking into expansion of services for Healthcare and Mental Health utilizing Western Iowa Transit (WIT). | Ongoing |  |  | “
6 | Chronic Disease Management | a | Continuing to develop processes / wellness screenings which support primary care and other providers in efforts to refer patients to care coordinators and health coaches. Promote Free Clinic and utilize the Care Manager | Ongoing | MRHC / New Opportunities / Pharmacy / Marketing | DOH / CCWellness Coalition, Schools, City, County, Law Enforcement. | “
|  | b | Explore grants and utilize grants funding for education and screening of Chronic Diseases. | Ongoing | Subcommittee: Shelby Dickson, Julie Hodne, Kimberly Vollstedt, Jackie Blackwell, Shelly Greving |  | “
|  | c | Continue a Reminder Program to encourage residents to visit their providers regularly for preventative screenings. | Ongoing |  |  | “
|  | d | Continue New Opportunities health education classes at schools, local areas, etc. (Lunch and Learns) with focus on hypertension, diabetes, smoking cessation, educate community on Health & Wellness practices, and chronic alcohol usage. | Ongoing |  |  | “
7 | Drug / Substance Abuse | a | Continue to provide counseling and support for drug abusers and their families. Treat them as patients who need health care instead of addicts. | Ongoing | MRHC/ Recovery Center / New Opportunities | DOH / CCWellness Coalition, Schools, City, County, Law Enforcement | “
|  | b | Collaborate with schools and churches to provide after-school programs and activity options to keep youth from developing habits involving drug / substance use. Start tobacco cessation education. | Ongoing | Subcommittee: Christy Jenkins, Taya Vonnahme |  | “
|  | c | Promote School DARE program to educate youth on the dangers of using drugs and alcohol. | Ongoing |  |  | “
|  | d | Continue clinic education on pain management. | Ongoing |  |  | “
|  | e | Continue to establish / promote discarding of old prescription drugs, especially opioids at the local hospital, pharmacy and police department. | Ongoing |  |  | “
|  | f | Explore supporting community substance abuse counseling. Establish / maintain a resource list for addiction treatment. (Adult & Youth). Communicate Recovery support system partners. | Ongoing |  |  | '
|  | g | Continue local advertisement / social media campaign to combat drug abuse. Explore communication options/materials to deploy meaningful message. | Ongoing |  |  | “
|  | h | Help support AA program through additional funding or communication of information to community members. | Ongoing |  |  | “
|  | i | Partner with local police authorities to develop a plan for individuals who have been found to drive while distracted/drunk. Require these individuals to take classes that emphasize the risk they put themselves/others at. | Ongoing |  |  | “
|  | j | Continue to build community awareness on drug abuse resources. Coordinate all community marketing activities among Stakeholders. Develop educational promotions (both digital & traditional handouts) for community. | Ongoing |  |  | “
|  | k | Start local campaign to combat parent hosting of underage drinking. Educate parents on ramifications. | Ongoing |  |  | '
|  | l | Research prevalent issues leading to drug abuse by adolescents. Work to establish systems to combat those issues. | Ongoing. New Opportunities is doing JADE Juvenile Alcohol & Drug Education. JADE is for youth ages 12-20. |  |  | “
|  | m | Explore & continue to host Substance Abuse Speakers @ schools assemblies / community events. | Ongoing |  |  | “
| Overall Estimated Cost for the Year |  |  | Updated by Julie Hodne RN CHNA Chairperson for MRHC 8-4-2023 |  |  | 7-1-2022 to 6-30-2023 | 5000

## KEYStakeholders
Key Area Stakeholders
KEY | Organization | Primary Contact
BH | Behavioral Health Providers -PSA
CCWC | Carroll County Wellness Coalition
Cham | Chamber / Mainstreet
City | PSA Cities
Clergy | Christ, Community and Celebrations - Organization
Clubs | Rotary, +++
CO | Carroll County
COLL | DMACC, Western Iowa Tech
DOH | Health Department
Drug / Alcohol | Manning Recovery Center
Ec Dev | Economic Development'
EMS | Emergency
Fed | US Federal Government
IA ST Ext | Iowa State University
IHA | Iowa Hospital Association
Large Empl | Large Employers in Carroll Co
Law Enf | PSA Sheriff / Police
LSC | Life skills Connections (Hollistic Health)
MRHC | Manning Regional Healthcare Center - Hospital
New Opp | New Opportunities - MH /All Care Company
Parks & Rec | PSA
Pharmacy
Rec Center | Manning Rec Center
Schools | PSA School Districts
Sr Care | Elder Bridge, Sr Life Solutions, Nursing Home, Assisted Living…